Fundamentals of Health Workflow Process Analysis and Redesign

Unit 10.7

Facilitating Implementation Decisions Meeting

Fall 2010

Slide 1:

Welcome to the Facilitating Implementation Decisions Meeting Unit.  This unit is from the Fundamentals of Health Workflow Process Analysis and Redesign component.  In one lecture, this unit covers the processes and logistics necessary for conducting the critical meeting in which Healthcare Setting personnel will review and streamline the redesigned process workflow diagram in preparation for implementing quality improvement and integrating the EHR. This unit provides the Health Care Workflow Analysis and Redesign Specialist with tools for conducting the meeting and initial plans for implementing the changes.

There are many methods for group facilitation.  Here, I will only discuss key concepts and provide references to resources that you can use as you develop your skills and portfolio of tools for meeting facilitation.

Slide 2:

Upon successful completion of this unit you should be able to:

  - Plan and conduct or facilitate a decision making meeting

  - Present a walk through of a decision making meeting

  - Prepare a presentation to communicate findings of a workflow process analysis to healthcare facility decision makers

  - Document those decisions that are made and actions identified in a decision making meeting.

By Describing the results of the process analysis and redesign conducted in the clinical setting, and Explaining how the health process analysis and redesign and meaningful use are related to the workflow process the workflow process analyst and redesign specialist should be able to lead the meeting participants through a discussion to:

  - Identify which of the clinical workflow component changes the clinic staff wants to implement

  - .Prioritize these changes

  - Identify participant roles in the change process, and

  - Describe how the new workflow processes might differ from the current processes

Slide 3:

The topics covered in Unit 7 of the Fundamentals of Health Workflow Process Analysis and Redesign Component include:

  - Coordinating a decision making meeting

  - Using appropriate group methods to discuss and make decisions on inefficiencies

  - Identifying opportunities for streamlining manual and computer-aided processes, and the

  - Transition from analysis and redesign to implementation planning, and we  will also give examples of the plan content.

In the analogy from Tom DeMarco, an early pioneer and thought leader in process analysis whose 1979 book, Structured Analysis and System Specification, was introduced in Unit one of this Component:  If “Procedure, like dance, resists description”; and individuals in process analysis and re-design jobs are experts at both “describing the dance”, and “choreographing a better one”; then the work of the Implementation Decision Making meeting is to not only “choreograph a better one”; but to streamline, refine, and optimize the “best workflow process design” for guiding the Quality Improvement.

Slide 4:

Many professional facilitators will agree with this quote:

“A single effective meeting will substantially
change the capacity of a group to
achieve desired outcomes”

To facilitate such a meeting requires good Leadership, a well planned Strategy, the appropriately selected group processes, and a good understanding of the culture of meeting participants, and finally, the coordination of these four layers.  When all of these come together the meeting enables the group to:
	Face the reality of the current process

Identify unused potential to improve,

and commit to action, or “Buy-in to the” Implementation Plan.

Slide 5:

The Goal is of the Implementations Decision Making meet is:  “ to make the healthcare process workflow as good or as effective as possible” by reviewing and streamlining the Workflow Diagrams generated in the Redesign effort and using the experience and skills of healthcare personnel involved in the processes to be streamlined.

We should recognize that the process changing is actually an ongoing effort.  This is because the requirements of the process are also changing.  It would be accurate to say that we are “ shooting at a moving target”.  The process requirements change because:

- The requirements of the customer (patient) change (increase)

- Technology changes (improves)

- The health care setting changes (treatment guidelines, new devices and drugs)

- The payment mechanisms change (medicaid/ medicare, and 3rd party payers).

This is all in the framework of “Meaningful Use” of Healthcare IT.

Slide 6:

At this point in the Process analysis and redesign we have,

Analyzed the “As is” Process and Redesigned the “As is” Process to create a Plan

We now have the “To be” Process

In this Unit we will discuss methods for working with the decision makers in the healthcare setting and leading them through discussions to determine which of the changes in the workflow process are important to implement, the priority of the implementation, and the specifics of the Quality Improvement process changes by:

- identifying areas for eliminating redundancy,

- streamlining patient and information flow, and

- identifying any wasted efforts that can be addressed.

One tool for this is the Patient Flow Diagram.

Remember:  The goal is to select the “best solution” to improve the processes.

Slide 7:

The Implementation Decision Making meeting has multiple purposes.  The primary purpose is to Streamline the Redesigned Workflow Diagrams.

In this way, the decisions made should:

    - Establish rapid, efficient information sharing,

    - Preserve established workflow when appropriate,

    - Build Consensus as necessary on the final redesign plans, and

    - Build “Buy In” of the participants to the changes proposed, AND finally,

    - Provide those decisions for the “Implementation” report

Slide 8:

Facilitation concerns itself with all the tasks needed to run a productive and impartial meeting. Facilitation serves the needs of any group who are meeting with a common purpose, whether it be making a decision, solving a problem, or simply exchanging ideas and information. The facilitator does not lead the group, nor does it try to distract or to entertain.  (Wikipedia)

As the decision-making / consensus building facilitator, the role of the Workflow Analysis and Redesign Specialist is to:

  - Establish Group Norms

  - Manage Time

  - Describe your role in the meeting

  - Describe the participants role in the meeting

  - Walk through the redesigned Process Workflow Diagrams

  - Establish ground rules for the meeting; i.e. How do you suggest changes?  How do you make decisions?

  - Listen to and document Feedback.  Active listening is critical because without listening too many errors will be made in the documentation and insufficient details will be provided in the implementation plan to address the needs of the process redesign.

Finally, the facilitator’s role is to:

  - Incorporate changes in the Process Diagrams and subsequently document these changes in a meeting report.

Slide 9:

The meeting participants are to:

Work within the established ground rules

- Suggest changes to the redesigned Process Workflow Diagrams

- Provide “reality checks”

- Identify:

  - Correction of any errors identified in the “To Be” process design

  - Reformatting (revision) needs of Workflow Diagrams

  - Training needs of new processes

It is expected that all participants will participate actively in the meeting

Slide 10:

There are so many methods of developing group consensus through meeting management that there is actually an internet site for selecting the best fit for the meeting’s needs

For our purposes it is sufficient to note the following key elements of success:

  - Involvement of key personnel who have thought through potential solutions

  - Involvement of key personnel results in ownership of ideas (solutions) and develops commitment for implementation

  - Immediate focus on changes which will make the greatest possible contribution to “Meaningful Use” and, the last element of success is the

  - Initial implementation planning is begun in a debriefing wrap-up session at the conclusion of the decision-making meeting

Slide 11:

We will only look at 3 methods of meeting facilitation here.  They are the focused conversation, consensus workshop and action planning methods.

The Focused Conversation Method is a common sense approach which leads naturally to a meaningful exchange of ideas.  This is more useful in Surfacing new ideas and solutions and Stimulating  candid feedback.

The Consensus Workshop Method will be helpful in this meeting.  This structured process is so engaging
people are energized getting to consensus.  Use it to

  - Tap rational and intuitive thought processes

  - Integrate diverse ideas

  - Generate practical and creative solutions

  - Develop group consensus

The Action Planning Method may also be helpful here.  These practical steps help groups plan, organize resources and build commitment.

• Visualize a successful result
• Analyze the current reality
• Create a practical plan
• Maximize group involvement

Slide 12:

Here, we address four aspects of facilitation.

The first is Making arrangements for the meeting. The practical arrangements will be arranged or managed by the facilitator. It is important to consider in detail the location and layout of the room, and understand why the meeting is being held and to assure that all stakeholders are invited and able to attend.

The second is Setting the agenda.  The facilitator needs to understand in detail how each item on the agenda is to be tackled and how long it should take and use techniques that will allow participants to understand all the issues at stake and all alternative courses of action.

Understanding group norms  will prevent the facilitator from making  assumptions about the way people interact and will enable you to adapt to the ways of different cultures and different organizations.

Understanding group dynamics will assure that the facilitator remains aware of undercurrents, both verbal and non-verbal, which may indicate problems the group is having. As the facilitator it is important that you try to assist the group in becoming aware of these.

Slide 13:

There are multiple approaches you can use to lead this discussion. The following approaches should be considered when planning the meeting.  The first is to Discuss the reformatting (revision) of Workflow Diagrams.  One way to do this is to Walk through the redesigned Process Workflow Diagrams and Incorporate changes in the Process Diagrams.  Also,

  - Provide Feedback on the Workflow Process Redesign

  - Discuss training needs of new processes

Slide 14:

As discussed earlier, the staff in these healthcare facilities are very busy people and the decision-making team may be coming in during their off time to participate in the meeting or they may be rescheduling patient care to work on this effort.  It is important to PREPARE carefully with great detail for this meeting in order to best use their very valuable time.

Thus,

Step 1:  Select participants for the Meeting

Step 2:  Prepare a detailed Agenda which should include;

- a Description of the proposed redesign (including goals)

- a Description of the to be the process and the gaps, as well as

- how group processes will be used to develop implementation plan, and the Test for consensus on decisions made

Step 3:  Prepare Review of the redesign reports

Step 4:  Develop exercise where each member of the Team independently writes down issues identified in the walkthrough of the process diagrams

Step 5:  Assure that Appropriate Settings and Materials are available: i.e. Flipcharts, Post It Notes, Markers, and plenty of Wall Space on which to post it.

Slide 15:

In this meeting, it is important to Identify processes Ripe for Improvement.

    - Those that can increase satisfaction, compliance, and meaningful use if health IT

    - Appeal to patients, clinicians and administrators

    - Some health care providers can show how much a change can improve services in specific areas

It is useful to Review “Best Practices” in other Health care facilities for items to discuss.  Best practice far exceeds health care service.

Slide 16:

This is an exercise to help the student recognize and identify processes that should be further analyzed as good candidates for process improvement.

In this exercise:

  - Identify topics ripe for Improvement in your organization (or use your current topic)

  - Once you have selected a topic, list specific ways in which each topic meets the selection criteria

- Define the gap (include outcome measure)

- Identify the good examples

- Identify business implications in your selected setting

Pause the slides now and complete this exercise.

Slide 17:

Kabcenell, Langley and Hupke in an IHI Innovation Series white paper, titled Innovations in Planned Care identified four key elements of the service delivery system as:

  - The care team

  - Patient activation

  - Clinical information systems, and

  - Leadership

They stated that “Only when all four aspects of the system are changed simultaneously can organizations produce better outcomes without increased costs.”

Consider categorizing your identified processes into these 4 areas as noted above.

Kabcenell AI, Langley J, Hupke C. Innovations in Planned Care. IHI Innovation Series white paper. Cambridge, MA: Institute for Healthcare Improvement; 2006. (Available on www.IHI.org)

Slide 18:

Group decision making is a Process.  A process which results in the selection of a course of action.

Decision making always Results in a “choice”.

There are multiple Systems of group decision making.  These include:

Consensus decision-making requires that a majority of the group approve a given course of action.  If the minority opposes the course of action, consensus systems require that the proposed actions be modified to remove or modify those features where there is lack of agreement until the entire group agrees on the plan.

Voting-based methods appropriate for this course include the following:

- Majority voting requires that more than 50% of the group members.  This implies that some members of the team will not agree with the course of action.

- Plurality, where the largest block of the group decides even if it is less than the majority, is not recommended for making the streamlining decisions and gaining “buy-in” of the team.

A Dictatorship is of course the state where one individual determines the course of action.

(Wikipedia

Slide 19:

It is important for the facilitator to analyze the culture and the decision-making style currently in the health care setting.

Discuss this with clinic to determine current and / or preferred decision making styles and incorporate this information into the meeting plans for decision making.

Slide 20:

In the health care field, the steps of making a decision may be remembered with the mnemonic BRAND, which includes

Benefits of the action

Risks of the action

Alternatives of the prospective action

Nothing: that is, doing nothing at all

Decision

http://en.wikipedia.org/wiki/Group_decision_making

Slide 21:

When conducting the meeting, be sure to Identify:

The Intent or purpose of  this meeting

The Working Assumptions of the meeting.  The Working Assumptions create an atmosphere of respect in the room without being moralistic with rules.  Some examples of working assumptions are:

- Everyone has knowledge that is valuable in this exercise

- We need everyone's input to create the best design

- There are no wrong answers or suggestions. The corollary, of course, is that there are no right answers or suggestions, only the best we can come up with given our limitations.

- The whole is greater than the sum of its parts.

- Everyone will listen to others and everyone will be heard.

It is also important to establish up front how much time will be needed and how the meeting will run.

Be aware that some people in group will not be willing to move at the pace of the slowest member.

In Unit 6, the important process changes and redesign were identified:

Walkthrough this information, question each step, make sure the meeting participants, decision makers, understand the who, what, when, where and how, and even why all decisions were made! In a walkthrough, you can identify the process gaps and inefficiencies, identify changes that are important and possible, and prioritize the changes in order of importance to that clinic.  Consider reviewing the process diagrams by performing a walkthrough from the perspective of each participant: the patient, the receptionist, the doctor, and others

It is important to:

  - Monitor the agenda / time

  - Encourage participation from all attendees

  - Help participants reach consensus / Foster solutions

Slide 22:

This is an exercise to help you start building a Toolbox of useful documents and aids for facilitating decision-making meetings in the health care setting.  Using the Patient Intake and Clinic Visit process in the following slide:

  - Create a meeting agenda to review this process, make decisions about what needs to be changed, and prioritize those decisions.

  - Design a form for capturing decisions agreed upon by the group.

  - After you do this, restart the slides and we will talk through the results.

Slide 23:

- Patient arrives at the clinic and signs-in and checks-in with the front desk.

- Receptionist enters the patient into the visit system as present and confirms the contact and insurance information with the patient.

- The nurse pulls the chart from the filing stacks and calls the patient to the exam area and escorts the patient to the exam room.

- The nurse interviews the patient regarding symptoms and/or complaints and records into the Nurses/Progress notes.

- Nurse takes and records vital signs in progress notes and alerts the Physician that the patient is ready to be seen.

- The Physician examines the patient and records findings in the progress notes.

- The Physician determines if a prescription, procedure, lab work or a referral is required and completes the necessary paperwork if applicable.

- The Physician provides any additional instructions to the patient and concludes the visit.

- The Physician provides the patient chart to the office staff for refiling.

- The office staff refiles the patient chart.

- The patient pays their co-pay and concludes the office visit.

Slide 24:

At the Global level, you will want to include at least the following items in the Agenda:

  - Introductions

  - Review of documentation of process analysis and redesign

  - Expected meeting Products

  - Closing or close-out of your meeting

Slide 25:

Depending on the size of the group and the complexity of the process redesign it is likely that a more detailed agenda will be required.

It is important to Introduce the Meeting, the participants in meeting and their role, and the Scope of Work for this meeting.

Also, the review of the redesigned process should include:

Mapping Methodology selection

Facilities Map

List of functions performed

Process Map of [key/ identified processes]

Personnel interviewed

All regulations associated with the redesign

Redesigned Workflow Diagram

Any process issues that are already known that will facilitate the discussion, and

Other supporting documents

Slide 26:

When planning for the Implementation decision making, focus the group on specific products expected from this meeting such as:

  - Immediately identifiable redundancies or inefficient processes

  - Quick wins or critical issues

  - Communication plan for identified or critical issues

  - Think about a Process Gap Analysis

  - An EHR Improvements Analysis

  - And the Recommendations

Finally, the meeting close should clearly identify meeting accomplishments and next steps.  Examples include:

      - Meeting Deliverables

  - Report

  - Report delivery date

  - Final Health Care Setting Implementation Plan

  - Report Dissemination

  - Implementation Strategy Selection

  - EHR Plan and Recommendations

Slide 27:

The following two slides include example forms for capturing decisions agreed upon in the meeting.  How do these compare with the ones you developed?

Slide 28:

This is one example of a table that can be used for capturing meeting results.  This focuses on the “As is” process, the “To be”, and the Responsible person for each of these actions.

Slide 29:

This is a second example that focuses on the “BRAND”: benefits, risks, alternatives, doing nothing, and decisions levels of reporting.

Slide 30:

Like “closing a sale” the wrap-up section of the meeting presents preliminary results and conclusions, secures “buy-in” and provides a prioritized plan for implementation.

Slide 31:

Finally, the meeting report provides complete documentation of all results

It should provide a concise Executive Summary of:

Objectives

Goals

Critical process issues

Results or Plans of the meeting.

Slide 32:

The final report should be long enough to address all details and decisions, provide sufficient information to justify the decisions, and lead the way forward.  It should:

- Be Sufficient to accomplish the change goals,

- Address only the redesign changes,

- It may be a good idea to Organize it by the Process Workflow Redesign,

- Be as specific as possible,

- Make recommendations actionable,

- Minimize redundancy (overlap), and

- Be Transparent.

Be sure to Validate decisions with the team

Identify General Process Improvement Opportunities

Slide 33:

In summary, this unit has

  - Provided strategies, tools, and aids for planning and conducting a decision making meeting

  - Presented examples of agenda and tables for conducting a walk through of a process, and

  - Provided tools for documenting decisions made and actions identified in a decision making meeting.

Additional strategies, tools, and aids for facilitating the implementation are presented in Unit 9 of this Component.

Slide 34:

These references were used in preparing this lecture